## Backlog
Task ID | Milestone | Task Name | Department | Primary AI Tool | Priority | Est. Mins | Status | Deliverable Target
TASK-01 | M1: Design & PM | Draft GDD & Physics Constants | Game Design | Google Antigravity | HIGH | 10 | DONE | docs/GDD.md [Example]
TASK-02 | M1: Design & PM | Export 16-Task Sprint Backlog CSV | Production | Google Antigravity | HIGH | 10 | DONE | Structured CSV imported to sheet
TASK-03 | M1: Design & PM | Define Modular File Architecture | Architecture | OpenCode CLI | HIGH | 10 | DONE | docs/ARCHITECTURE.md module tree
TASK-04 | M2: Core 3D Engine | Initialize Vite + Three.js Scene | Engineering | OpenCode CLI | HIGH | 10 | IN PROGRESS | 60 FPS WebGL canvas + chase cam
TASK-05 | M2: Core 3D Engine | Build CatmullRomCurve3 Circuit | Engineering | Google Antigravity | HIGH | 15 | PENDING | Closed asphalt loop + curbs
TASK-06 | M2: Core 3D Engine | Code Arcade Raycast Kart Physics | Engineering | Google Antigravity | HIGH | 15 | PENDING | Thrust, reverse, off-road drag
TASK-07 | M2: Core 3D Engine | Implement Spacebar Drift & Turbo | Engineering | OpenCode CLI | HIGH | 15 | PENDING | 1.0s drift charge awards boost
TASK-08 | M2: Core 3D Engine | Add Speed Pads & Item Boxes | Gameplay | Google Antigravity | MEDIUM | 15 | PENDING | 4 speed pads + 6 item boxes
TASK-09 | M2: Core 3D Engine | Code Waypoint AI Rival Karts | AI Systems | OpenCode CLI | MEDIUM | 10 | PENDING | 2 AI rivals racing 3 laps
TASK-10 | M3: 3D Assets (MCP) | Connect Blender MCP Server | 3D Art | MCP for Blender | HIGH | 10 | PENDING | uvx mcp-for-blender active
TASK-11 | M3: 3D Assets (MCP) | Model Low-Poly Cyber Kart Mesh | 3D Art | MCP for Blender | HIGH | 15 | PENDING | Export public/assets/kart.glb
TASK-12 | M3: 3D Assets (MCP) | Generate Custom Track Archway | 3D Art | Meshy / Tripo3D | LOW | 10 | PENDING | Export public/assets/arch.glb
TASK-13 | M4: Audio & HUD | Synthesize Web Audio Engine SFX | Audio | Google Antigravity | MEDIUM | 10 | PENDING | Oscillator pitch tied to speed
TASK-14 | M4: Audio & HUD | Extract Local BGM via yt-dlp CLI | Audio | yt-dlp / Suno | LOW | 10 | PENDING | Local bgm.mp3 + CC0 prod swap
TASK-15 | M5: UI & Deploy | Build Racing HUD & Lap Timer | UI/UX | Google Antigravity | HIGH | 5 | PENDING | Speedometer, Lap 1/3, Item UI
TASK-16 | M5: UI & Deploy | Deploy Static Build to Web Host | DevOps | OpenCode CLI | MEDIUM | 10 | PENDING | GitHub Pages / Vercel live URL
TOTAL | All 5 Lab Milestones | 16 Scheduled Tasks | Solo Builder | Multi-Agent Stack | HIGH | 180 | IN PROGRESS | Complete 180-Min Lab Scope

## Milestone Schedule
Milestone | Lab Window | Tasks [Auto] | Done [Auto] | Mins [Auto] | Progress [Auto] | Checkpoint Deliverable
M1: Design & PM | 0:00 - 1:00 | 3 | 3 | 30 | 100% | GDD, Architecture & Backlog
M2: Core 3D Engine | 1:00 - 2:00 | 6 | 0 | 80 | 0% | Playable Three.js Kart Prototype
M3: 3D Assets (MCP) | 2:00 - 2:30 | 3 | 0 | 35 | 0% | Custom Blender MCP .glb Assets
M4: Audio & HUD | 2:30 - 2:45 | 2 | 0 | 20 | 0% | Web Audio SFX + yt-dlp Local BGM
M5: UI & Deploy | 2:45 - 3:00 | 2 | 0 | 15 | 0% | Racing HUD + GitHub Pages Deploy
Total Workshop | 3 Hours (180m) | 16 | 3 | 180 | 18.75% | Playable 3D Web Kart Racer

## AI Prompt Primer
Workflow Phase | Target AI Tool | Agent Objective | Expected Output | Target Sheet Range
1. Mechanics to Epics | Google Antigravity | Decompose GDD into 5 Lab Epics | 5 Milestone Epics Table | Milestone Schedule (A2:B6)
2. Epics to Sprint CSV | OpenCode CLI / Antigravity | Generate 16 atomic 10-15 min solo builder tasks in docs/BACKLOG.csv matching columns A-I | RFC-4180 CSV file in repo | Backlog (A2:I17)
3. Physics Constant Sync | OpenCode CLI | Verify every handling parameter in docs/GDD.md matches src/config/constants.js | Verified constants & slider UI | Mark TASK-06 & TASK-07 DONE
4. Blender MCP Export | MCP for Blender | Procedurally build low-poly Cyber Kart (<3,500 tris) and export binary kart.glb | public/assets/models/kart.glb | Mark TASK-10 to TASK-12 DONE
5. Scope Triage Check | Google Antigravity | Filter PENDING tasks with 30 mins left and enable procedural fallbacks for LOW priority items | Prioritized cut-list & fallback | Filter Priority = HIGH